## GanttChart
Gantt Chart Template | [5 empty] | © 2006-2014 Vertex42.com | FALSE | 1 | 1 | 2 | [Hide this row]
PROJECT NAME
SCK Contractors
| Project Lead: |  |  | YOUR NAME
| Project Start Date: |  |  | 2023-10-01 |  |  | Project Weeks: |  | 12.5 |  | Weeks
| Today's Date: | [8 empty] | [42]
Calculated End Date:
WBS | ↓↓↓↓ Task ↓↓↓↓ | Lead | Predecessors |  | End | Work Days | % Done | Cal Days | Days Done | Days Left | Color
| Project Duration | [9 empty] | k
Project Start to Finish
1 | Mobilization |  |  |  |  | 1 | 0%
2 | walls |  |  | 2022-07-05 |  | 1 | 0%
3 | HVAC Install Duct and unit |  |  | 2022-07-05 |  | 3 | 0%
4 | GPR/Send to Structural Engineer |  |  | 2022-07-08 |  | 2 | 0%
5 | Concrete Raised floor layout |  |  | 2022-07-12 |  | 2 | 0%
6 | Install Rebar and foam |  |  | 2022-07-14 |  | 3 | 0%
7 | Install Electric thru foam |  |  | 2022-07-19 |  | 1 | 0%
8 | Inspection for Floor Close in |  |  | 2022-08-18 |  | 1 | 0%
9 | Pour Concrete |  |  | 2022-08-19 |  | 1 | 0%
10 | Wall Layout & Framing |  |  | 2022-08-22 |  | 2 | 0%
11 | Plumbing Rough In |  |  | 2022-08-24 |  | 3 | 0%
12 | Electrical rough in |  |  | 2022-08-24 |  | 3 | 0%
13 | Drywall Installation |  |  | 2022-08-29 |  | 3 | 0%
14 | Wall close in inspection |  |  | 2022-09-01 |  | 1 | 0%
15 | Drywall Close in |  |  | 2022-09-01 |  | 5 | 0% |  | 0
16 | Polish floors |  |  | 2022-09-15 |  | 2 | 0%
17 | Ceiling Layout & Tile Install |  |  | 2022-09-21 |  | 1 | 0%
18 | Paint |  |  | 2022-09-21 |  | 2 | 0%
19 | Electrical Trim out |  |  | 2022-09-22 |  | 3 | 0%
20 | Millwork Install |  |  | 2022-09-22 |  | 3 | 0%
21 | Plumbing Trim out |  |  | 2022-09-22 |  | 3 | 0%
22 | Sprinkler Rough In & Trim out |  |  | 2022-09-22 |  | 1 | 0%
21 | Conveyor Install |  |  | 2022-09-23 |  | 2 | 0%
22 | Final Inspection |  |  | 2022-09-27 |  | 1 | 0%
23 | Final clean and punch list |  |  | 2022-09-28 |  | 3 | 0%
Note on I1: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on J1: Show 7 Day Week: 1 = true 0 = false
Note on K1: Scroll-Bar Cell Link: Starting day, week, or month. (Added to the Project start date).
Note on L1: Display Mode: This value is set via the drop-down field.
Note on M1: Start of Work Week: Sunday = 1 :: weekend is defined as Friday & Saturday Monday = 2 :: weekend is defined as Saturday & Sunday
Note on B6: Project Start Date Enter the Start Date for the Project. Avoid choosing a date that falls on a Saturday or Sunday.
Note on B7: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on A9: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B9: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C9: Task Lead Enter the name of the Task Lead in this column.
Note on D9: Predecessor Tasks [ You can hide these columns if you are not going to use them ] Use a formula like =A15 to reference the WBS of the Predecessor Task that must be completed before this task can start. Doing so will help ensure that if you move the task, the dependency will remain correct. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor.
Note on G9: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1,holidays) to set the Start date to the next work day (excluding weekends and holidays), where enddate is the cell reference for the End date of the Predecessor task.
Note on H9: End Date The WORKDAY() function is used to calculate the ending date so that the End Date does not fall on a weekend or a holiday. If you choose to use the Duration as the input, the End date is calculated as the Start date + Duration - 1.
Note on I9: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude Saturday and Sunday and holidays listed in the Holidays worksheet.
Note on J9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K9: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on L9: Calendar Days Complete [ You can hide this column prior to printing ] This column is calculated by multiplying the Work Days by the %Complete and using the WORKDAY() function to determine how many calendar days have been completed. Note: The conditional formatting used to create the gantt chart references this column.
Note on M9: Calendar Days Remaining [ You can hide this column prior to printing ] This column is calculated by subtracting the Days Complete from the Duration.
Note on N9: Color (Optional): Enter a color code in this column to change the color of the incomplete portion of the gantt chart. 1 - 6 = theme-based accent colors k = black r = red o = orange y = yellow p = purple g = green

## GanttChart-BETA
Gantt Chart Template | [5 empty] | TRUE |  | © 2013 Vertex42.com | FALSE | 1 | 2 | 2 | [Hide this row]
[Project Name] Project Schedule
[Company Name]
| Project Lead: |  |  | [ Name of Lead ]
| Project Start Date: |  |  | 2014-01-01
| Today's Date: | [10 empty] | [42]
WBS | Task | Lead | Predecessors | Start | End | Original Start | Original End | Work Days | % Done | Cal Days | Days Done | Days Left | Color
| Project Duration | [11 empty] | k
| [ Task Category ] | [ name ] |  |  |  | 2014-01-01 | 2014-03-20
| [ Level 2 Task ] |  |  | 2014-01-05 |  | 2014-01-01 | 2014-01-01 | 1 | 25%
| [ Level 2 Task ] |  |  |  |  | 2014-01-02 | 2014-01-03 | 2 | 25%
| [ Level 2 Task ] |  |  |  |  | 2014-01-04 | 2014-01-08 | 3 | 25%
| [ Level 2 Task ] |  |  |  |  | 2014-01-09 | 2014-01-14 | 4 | 25%
| [ Level 2 Task ] |  |  |  |  | 2014-01-15 | 2014-01-22 | 5 | 25% |  |  |  | g
| [ Level 2 Task ] |  |  |  |  | 2014-01-23 | 2014-01-30 | 6 | 25% |  |  |  | y
| [ Level 2 Task ] |  |  |  |  | 2014-01-31 | 2014-02-10 | 7 | 25% |  |  |  | o
| [ Level 2 Task ] |  |  |  |  | 2014-02-11 | 2014-02-21 | 6 | 25% |  |  |  | p
| [ Level 2 Task ] |  |  |  |  | 2014-02-22 | 2014-03-06 | 9 | 25% |  |  |  | k
| [ Level 2 Task ] |  |  |  |  | 2014-03-07 | 2014-03-20 | 6 | 25% |  |  |  | r
[Insert Rows above this one, then Hide or Delete this row]
| [ Task Category ] | [ name ] |  |  |  | 2014-01-01 | 2014-03-20
| [ Level 2 Task ] |  |  |  |  | 2014-01-01 | 2014-01-01 | 1
| [ Level 2 Task ] |  |  |  |  | 2014-01-02 | 2014-01-03 | 2
| [ Level 2 Task ] |  |  |  |  | 2014-01-04 | 2014-01-08 | 3
| [ Level 2 Task ] |  |  |  |  | 2014-01-09 | 2014-01-14 | 4
| [ Level 2 Task ] |  |  |  |  | 2014-01-15 | 2014-01-22 | 5 |  |  |  |  | g
| [ Level 2 Task ] |  |  |  |  | 2014-01-23 | 2014-01-30 | 10 |  |  |  |  | y
| [ Level 2 Task ] |  |  |  |  | 2014-01-31 | 2014-02-10 | 12 |  |  |  |  | o
| [ Level 2 Task ] |  |  |  |  | 2014-02-11 | 2014-02-21 | 14 |  |  |  |  | p
| [ Level 2 Task ] |  |  |  |  | 2014-02-22 | 2014-03-06 | 15 |  |  |  |  | k
| [ Level 2 Task ] |  |  |  |  | 2014-03-07 | 2014-03-20 | 20 |  |  |  |  | r
[Insert Rows above this one, then Hide or Delete this row]
| [ Task Category ] | [ name ]
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
[Insert Rows above this one, then Hide or Delete this row]
| [ Task Category ] | [ name ]
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
| [ Level 2 Task ] | [6 empty] | 1
[Insert Rows above this one, then Hide or Delete this row]
TEMPLATE ROWS
Use the rows listed below by Copying/Pasting the entire row, or the cells from columns C through Q.
To change the WBS level, you only need to copy & paste the relevant WBS cell in column A.
To use the rows with Predecessors as the inputs, unhide columns D through F
{42}
WBS Numbering & Label-only Rows
[ Task Category ]
[ Level 2 Task (label only) ]
[ Level 3 Task (label only) ]
[ Level 4 task (label only) ]
WORK DAYS: These rows are used to exclude weekends and holidays
| [ Task Summary ] | [ name ]
| [ Start date and End date ] | [11 empty] | k
[ Start date and Work Days ]
[ Predecessors and Work Days ]
[ Predecessors and End date ]
CALENDAR DAYS: Use these rows if weekends and holidays need to be included
| [ Task Summary ] | [ name ]
| [ Start date and End date ] | [11 empty] | k
[ Start date and Calendar Days ]
| [ Predecessors and Calendar Days ] | [8 empty] | 1
[ Predecessors and End date ]
Formula to copy/paste for color-coding based on urgency (see help):
Formula to copy/paste for color-coding based on task lead (see help):
Combined (urgency first, task lead second):
Note on I1: Show Original Dates: 1 = true 0 = false
Note on K1: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on L1: Show 7 Day Week: 1 = true 0 = false
Note on M1: Scroll-Bar Cell Link: Starting day, week, or month. (Added to the Project start date).
Note on N1: Display Mode: This value is set via the drop-down field.
Note on O1: Start of Work Week: Sunday = 1 :: weekend is defined as Friday & Saturday Monday = 2 :: weekend is defined as Saturday & Sunday
Note on B6: Project Start Date Enter the Start Date for the Project. Avoid choosing a date that falls on a Saturday or Sunday.
Note on B7: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on A8: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B8: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C8: Task Lead Enter the name of the Task Lead in this column.
Note on D8: Predecessor Tasks Use a formula like =A15 to reference the WBS of the Predecessor Task that must be completed before this task can start. Doing so will help ensure that if you move the task, the dependency will remain correct. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor.
Note on G8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1,holidays) to set the Start date to the next work day (excluding weekends and holidays), where enddate is the cell reference for the End date of the Predecessor task.
Note on H8: End Date The WORKDAY() function is used to calculate the ending date so that the End Date does not fall on a weekend or a holiday. If you choose to use the Duration as the input, the End date is calculated as the Start date + Duration - 1.
Note on I8: Original Start: After creating your gantt chart, copy the Start dates into this column but PASTE VALUES ONLY. This will be used as a reference so that you can see the difference between the original plan and the actual dates. Tip: You may want to hide this column after entering the original dates.
Note on J8: Original End: After creating your gantt chart, copy the End dates into this column but PASTE VALUES ONLY. This will be used as a reference so that you can see the difference between the original plan and the actual dates. Tip: You may want to hide this column after entering the original dates.
Note on K8: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude Saturday and Sunday and holidays listed in the Holidays worksheet.
Note on L8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on M8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on N8: Calendar Days Complete This column is calculated by multiplying the Work Days by the %Complete and using the WORKDAY() function to determine how many calendar days have been completed. Note: The conditional formatting used to create the gantt chart references this column.
Note on O8: Calendar Days Remaining This column is calculated by subtracting the Days Complete from the Duration.
Note on P8: Color (Optional): Enter a color code in this column to change the color of the incomplete portion of the gantt chart. 1 - 6 = theme-based accent colors k = black r = red o = orange y = yellow p = purple g = green

## GanttChart_Example
Gantt Chart Template | [5 empty] | © 2013 Vertex42.com | FALSE | 1 | 1 | 2 | [Hide this row]
[Project Name] Project Schedule
[Company Name]
| Project Lead: |  |  | [ Name of Lead ]
| Project Start Date: |  |  | 2013-03-05
| Today's Date: |  |  | 2013-03-07 | [5 empty] | [42]
WBS | Task | Lead | Predecessors | Start | End | Work Days | % Done | Cal Days | Days Done | Days Left | Color
| [ Task Category ] | [ name ] | [8 empty] | k
| [ Level 2 Task ] | [name] |  | 2013-03-05 |  | 10 | 50%
| [ Level 2 Task ] | [name] |  | 2013-03-07 |  | 15 | 50% |  |  |  | r
| Level 2 |  |  | 2013-03-09 |  | 20 | 50% |  |  |  | g
| Level 3 |  |  | 2013-03-13 |  | 15 |  |  |  |  | p
| Level 3 |  |  | 2013-03-20 |  | 5 |  |  |  |  | o
| Level 4 |  |  | 2013-03-27 |  | 1 |  |  |  |  | k
| Level 4 |  |  | 2013-04-03 |  | 8 |  |  |  |  | 1
| [ Level 3 Task ] |  |  | 2013-04-10 |  | 8 |  |  |  |  | 2
| [ Level 2 Task ] |  |  | 2013-04-17 |  | 8 |  |  |  |  | 3
| [ Level 2 Task ] |  |  | 2013-04-24 |  | 21 |  |  |  |  | 4
| [ Level 2 Task ] |  |  | 2013-05-01 |  | 21 |  |  |  |  | 5
| [ Level 2 Task ] |  |  | 2013-05-08 |  | 21 |  |  |  |  | 6
[Insert Rows above this one, then Hide or Delete this row]
| [ Color-Coding by Urgency ] | [ name ]
| [ Level 2 Task ] |  |  | 2013-03-05 |  | 4 | 50%
| [ Level 2 Task ] |  |  |  |  | 4 | 50%
| [ Level 2 Task ] |  |  |  |  | 4 | 50%
| [ Level 2 Task ] |  |  |  |  | 4 | 100%
| [ Level 2 Task ] |  |  |  |  | 4 | 100%
| [ Level 2 Task ] |  |  |  |  | 4 | 100%
| [ Level 2 Task ] |  |  |  |  | 4 | 50%
| [ Level 2 Task ] |  |  |  |  | 4 | 50%
| [ Level 2 Task ] |  |  |  |  | 4 | 50%
| [ Level 2 Task ] |  |  |  |  | 4 | 50%
[Insert Rows above this one, then Hide or Delete this row]
| [ Color-Coding by Lead Name ] | [ name ]
| [ Level 2 Task ] | Sarah |  | 2013-03-05 |  | 21
| [ Level 2 Task ] | Bill |  |  |  | 21
| [ Level 2 Task ] | Bob |  |  |  | 21
| [ Level 2 Task ] | Jim |  |  |  | 21
| [ Level 2 Task ] | Sarah |  |  |  | 21
| [ Level 2 Task ] | Bill |  |  |  | 21
| [ Level 2 Task ] | Bob |  |  |  | 21
| [ Level 2 Task ] | Jim |  |  |  | 21
| [ Level 2 Task ] | Sarah |  |  |  | 21
| [ Level 2 Task ] | Bill |  |  |  | 21
[Insert Rows above this one, then Hide or Delete this row]
| [ Combined Color-Coding ] | [ name ]
| [ Level 2 Task ] | Sarah |  | 2013-03-05 |  | 10
| [ Level 2 Task ] | Bill |  |  |  | 10
| [ Level 2 Task ] | Bob |  |  |  | 10
| [ Level 2 Task ] | Jim |  |  |  | 2
| [ Level 2 Task ] | Sarah |  |  |  | 2
| [ Level 2 Task ] | Bill |  |  |  | 10
| [ Level 2 Task ] | Bob |  |  |  | 6
| [ Level 2 Task ] | Jim |  |  |  | 14
| [ Level 2 Task ] | Sarah |  |  |  | 5
| [ Level 2 Task ] | Bill |  |  |  | 4
[Insert Rows above this one, then Hide or Delete this row]
TEMPLATE ROWS
Use the rows listed below by Copying/Pasting the entire row, or the cells from columns C through O.
To change the WBS level, you only need to copy & paste the relevant WBS cell in column A.
To use the rows with Predecessors as the inputs, unhide columns D through F
{42}
WBS Numbering & Label-only Rows
[ Task Category ]
[ Level 2 Task (label only) ]
[ Level 3 Task (label only) ]
[ Level 4 task (label only) ]
WORK DAYS: These rows are used to exclude weekends and holidays
| [ Task Summary ] | [ name ]
| [ Start date and End date ] | [9 empty] | k
[ Start date and Work Days ]
[ Predecessors and Work Days ]
[ Predecessors and End date ]
CALENDAR DAYS: Use these rows if weekends and holidays need to be included
| [ Task Summary ] | [ name ]
| [ Start date and End date ] | [9 empty] | k
[ Start date and Calendar Days ]
[ Predecessors and Calendar Days ]
[ Predecessors and End date ]
Formula to copy/paste for color-coding based on urgency (see help):
Formula to copy/paste for color-coding based on task lead (see help):
Combined (urgency first, task lead second):
Note on I1: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on J1: Show 7 Day Week: 1 = true 0 = false
Note on K1: Scroll-Bar Cell Link: Starting day, week, or month. (Added to the Project start date).
Note on L1: Display Mode: This value is set via the drop-down field.
Note on M1: Start of Work Week: Sunday = 1 :: weekend is defined as Friday & Saturday Monday = 2 :: weekend is defined as Saturday & Sunday
Note on B6: Project Start Date Enter the Start Date for the Project. Avoid choosing a date that falls on a Saturday or Sunday.
Note on B7: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on A8: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B8: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C8: Task Lead Enter the name of the Task Lead in this column.
Note on D8: Predecessor Tasks Use a formula like =A15 to reference the WBS of the Predecessor Task that must be completed before this task can start. Doing so will help ensure that if you move the task, the dependency will remain correct. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor.
Note on G8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1,holidays) to set the Start date to the next work day (excluding weekends and holidays), where enddate is the cell reference for the End date of the Predecessor task.
Note on H8: End Date The WORKDAY() function is used to calculate the ending date so that the End Date does not fall on a weekend or a holiday. If you choose to use the Duration as the input, the End date is calculated as the Start date + Duration - 1.
Note on I8: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude Saturday and Sunday and holidays listed in the Holidays worksheet.
Note on J8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on L8: Calendar Days Complete This column is calculated by multiplying the Work Days by the %Complete and using the WORKDAY() function to determine how many calendar days have been completed. Note: The conditional formatting used to create the gantt chart references this column.
Note on M8: Calendar Days Remaining This column is calculated by subtracting the Days Complete from the Duration.
Note on N8: Color (Optional): Enter a color code in this column to change the color of the incomplete portion of the gantt chart. 1 - 6 = theme-based accent colors k = black r = red o = orange y = yellow p = purple g = green

## Holidays
Holidays to Exclude from Work Days
List special dates that should be considered non-working days. You do not need to list weekends because the NETWORKDAYS() and WORKDAY() functions already exclude weekends.
If your project spans more than one year, add separate dates for each holiday for each year.
Date | Description
2012-12-25 | Christmas
2013-12-25 | Christmas
2014-12-25 | Christmas
2015-12-25 | Christmas
2016-12-25 | Christmas
2017-12-25 | Christmas
2018-12-25 | Christmas
2019-12-25 | Christmas
2020-12-25 | Christmas
2021-12-25 | Christmas
2022-12-25 | Christmas
2012-10-08 | Columbus Day
2013-10-14 | Columbus Day
2014-10-13 | Columbus Day
2015-10-12 | Columbus Day
2016-10-10 | Columbus Day
2017-10-09 | Columbus Day
2018-10-08 | Columbus Day
2019-10-14 | Columbus Day
2020-10-12 | Columbus Day
2021-10-11 | Columbus Day
2022-10-10 | Columbus Day
2012-07-04 | Independence Day
2013-07-04 | Independence Day
2014-07-04 | Independence Day
2015-07-04 | Independence Day
2016-07-04 | Independence Day
2017-07-04 | Independence Day
2018-07-04 | Independence Day
2019-07-04 | Independence Day
2020-07-04 | Independence Day
2021-07-04 | Independence Day
2022-07-04 | Independence Day
2012-09-03 | Labor Day
2013-09-02 | Labor Day
2014-09-01 | Labor Day
2015-09-07 | Labor Day
2016-09-05 | Labor Day
2017-09-04 | Labor Day
2018-09-03 | Labor Day
2019-09-02 | Labor Day
2020-09-07 | Labor Day
2021-09-06 | Labor Day
2022-09-05 | Labor Day
2012-01-16 | M.L.King Jr. Day
2013-01-21 | M.L.King Jr. Day
2014-01-20 | M.L.King Jr. Day
2015-01-19 | M.L.King Jr. Day
2016-01-18 | M.L.King Jr. Day
2017-01-16 | M.L.King Jr. Day
2018-01-15 | M.L.King Jr. Day
2019-01-21 | M.L.King Jr. Day
2020-01-20 | M.L.King Jr. Day
2012-05-28 | Memorial Day
2013-05-27 | Memorial Day
2014-05-26 | Memorial Day
2015-05-25 | Memorial Day
2016-05-30 | Memorial Day
2017-05-29 | Memorial Day
2018-05-28 | Memorial Day
2019-05-27 | Memorial Day
2020-05-25 | Memorial Day
2012-01-01 | New Year's Day
2013-01-01 | New Year's Day
2014-01-01 | New Year's Day
2015-01-01 | New Year's Day
2016-01-01 | New Year's Day
2017-01-01 | New Year's Day
2018-01-01 | New Year's Day
2019-01-01 | New Year's Day
2020-01-01 | New Year's Day
2012-02-20 | Presidents Day
2013-02-18 | Presidents Day
2014-02-17 | Presidents Day
2015-02-16 | Presidents Day
2016-02-15 | Presidents Day
2017-02-20 | Presidents Day
2018-02-19 | Presidents Day
2019-02-18 | Presidents Day
2020-02-17 | Presidents Day
2010-11-25 | Thanksgiving
2011-11-24 | Thanksgiving
2012-11-22 | Thanksgiving
2013-11-28 | Thanksgiving
2014-11-27 | Thanksgiving
2015-11-26 | Thanksgiving
2016-11-24 | Thanksgiving
2017-11-23 | Thanksgiving
2018-11-22 | Thanksgiving
2019-11-28 | Thanksgiving
2020-11-26 | Thanksgiving
2012-11-11 | Veterans Day
2013-11-11 | Veterans Day
2014-11-11 | Veterans Day
2015-11-11 | Veterans Day
2016-11-11 | Veterans Day
2017-11-11 | Veterans Day
2018-11-11 | Veterans Day
2019-11-11 | Veterans Day
2020-11-11 | Veterans Day

## Help
Gantt Chart Template
INSTRUCTIONS |  | © 2006-2014 Vertex42 LLC
| If this page does not answer your questions, visit the following page: | Support
Intro
The Vertex42® Gantt Chart Template is designed to make creating a project schedule very
simple. You only need to know some very basic Excel techniques to make this gantt chart
work for you, such as how to copy and paste entire rows. Be sure to read the Getting Started
Tips below.
Cell Color Key
Input Cell | :: Indicates which set of inputs to use
Formula to Edit | :: Indicates formulas you may need to verify
Incomplete Task | :: In the Gantt chart, indicates the incomplete portion of the task
Completed Task | :: In the Gantt chart, indicates the completed portion of the task
Getting Started Tips
Watch the Demo Videos
| • Input cells have a light green background. | Input Cell
| • Cells with a darker green background are formulas you may need to verify and edit. | Formula to Edit
When you insert new rows or move rows around, you should double-check these formulas.
• [ Bracketed Text ] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments (marked with little red triangles) to provide | Label
extra help information.
• The Project Start Date determines the first week shown in the gantt chart, and may
also be referenced by some tasks, so be careful when changing it.
• Instead of changing the Project Start Date, use the slider bar to adjust the range of dates
shown in the gantt chart.
• The red line in the gantt chart represents the date in the Today's Date cell.
You can enter Today's Date manually or use the formula =TODAY()
The range of dates displayed is limited by the number of columns in Excel 2003.
Excel 2007 lets you increase the number of columns. See the FAQ below.
• To insert additional tasks, copy an exising row from the selection of Template Rows at
the bottom of the worksheet.
• Edit the Holidays worksheet to choose which dates you want to exclude from Work Days.
• If you see "#####" in a cell, widen the COLUMN to display the cell contents.
• This workbook uses a lot of conditional formatting. Look up "conditional formatting" in the
Excel help system (F1) if you want to know how it works.
• Backup your file regularly to avoid losing data! Excel files DO get corrupted occasionally.
Changing the Display Mode from Daily to Weekly to Monthly
| Use the drop-down field to change the display of the gantt chart to daily, weekly, or monthly. | Daily
| NOTE: When using the monthly view, the LENGTH of the bar in the gantt chart does not | Weekly
| represent a true relative duration because each month has a different number of days, and | Monthly
each column shows a 4-day period (except for the last column in the month, which is variable).
Show Weekends: When using the Daily display, check the "Show Weekends" box if you want to
show Saturday and Sunday in the gantt chart.
Using the Template Rows for Different Sets of Inputs
There are many ways to define the Start Date, End Date, and Duration of a task. Sometimes
you may want to enter the Start date manually, and other times you may want to calculate the
Start date based on the End date of another task. The most common way to define the
duration of a task is by entering the number of Work Days, but for some tasks you may want
to choose the End date. The template rows at the bottom of the gantt chart are designed to
let you choose the set of inputs you want to use for a particular task.
Remember: Inputs are the light green cells.
To use a Template Row:
Note: Use row operations by right-clicking on the Row #
1. Copy the row you want to use.
2. Right-click on the row below where you want to insert the new task and select Insert Copied Cells
3. Find a cell containing the WBS level you want to use, then copy and paste from that cell.
Changing WBS Numbering
The WBS numbering uses a different formula for each level, but the formula does not reference
any other cell in the row. So, you can copy and paste just the WBS cell that you want to use.
Note: If you leave a blank cell above a WBS number, the numbering will reset to 0.x.x
Category Tasks and Tasks Defined by Sub-Tasks
You can use tasks that are just labels, but it can also be useful for the category task to display
the minimum Start date and maximum End date of its sub tasks. To do this, use the formulas:
=MIN(startdates_of_subtasks) and =MAX(enddates_of_subtasks)
The % Complete for the summary task can be calculated using the following formula:
=SUMPRODUCT( workdays_range, percentcomplete_range) / SUM(workdays_range)
where workdays_range references the range of cells for the sub taks in the Work Days column,
and percentcomplete_range references the range of cells in the % Done column.
The "Task Summary" template rows provide examples of these formulas.
Changing the set of inputs for a task that is already defined
If you already have a row with the WBS and task description entered, and you just want to
change which set of inputs to use (e.g. Start/End instead of Start/Workdays), you do not
necessarily need to copy/paste an entire template row over the top of your existing task.
Instead, you can copy/paste just the cells in columns D through N from the appropriate
template row.
Creating Task Dependencies
Using Your Own Custom Formulas
You can enter the Start date manually, or define your own dependecies using a formula.
You should use a Template Row where the Start date is highlighted green (to indicate that it
is an input), as in rows 12 and 13 shown below.
Below are the most common options for entering the Start date:
A. Enter the date manually (e.g. 1/3/2011)
B. Reference the Project Start Date (e.g. =$G$7 )
C. Set the Start date to the next Work Day after another task's End date
This is the example shown in the screenshot above: =WORKDAY(enddate,1,holidays)
where enddate is the reference to the End date of task 1.1 and "holidays" is a named range
that refers to the list in the Holidays worksheet.
For multiple predecessors, the formula would be:
=MAX( WORKDAY(enddate1,1,holidays), WORKDAY(enddate2,1,holidays) )
D. Set the Start date to the next Calendar Day after another task's End date.
This formula is even simpler: =enddate+1
For multiple predecessors, the formula would be:
=MAX( enddate1, enddate2, enddate3 ) + 1
E. Set the Start date to a number of days before or after another date.
This formula is just like the one in C or D, except that in place of the "1" you enter the
number of days, such as =WORKDAY(enddate, 5, holidays) or =WORKDAY(startdate, -5, holidays)
Using the Predecessor Columns
- The predecessor columns and the template rows that use them, are hidden by default.
They use a special formula for the task Start date that allows you to make the start date
depend on the End date of another task by just referencing the WBS of that task.
1. Reference a Predecessor using a formula.
The screenshot below shows how to use a formula to set task 1.3.1 as a Predecessor for
task 1.4. Press "=" then click on the cell containing the WBS you want to reference. This
method is preferred because if you move rows around, the reference will adjust.
2. Enter the Predecessor manually as text.
You can enter the Predecessor manually, but you must make sure that you enter it as text,
or you will end up with a bunch of #NA errors. To enter 1.3 as text, just add an apostrophe
at the beginning like this: '1.3.
Note: This is not the best method, because if you insert a new task, you'll have to update
all of the Predecessors again, or at least verify that they are still correct.
Color-Coding the Bars of the Gantt Chart
The Color column is a new feature available only in this new Excel 2007+ version of Gantt Chart
Template Pro. This version has been configured to allow you to change the colors of the
bars in the chart area by entering a color code into the Color column. The codes include:
k (black), r (red), o (orange), y (yellow), p (purple), g (green), 1 - 6 (theme-based accent colors)
| How it Works … |  | Names | Color
| The chart area uses conditional formatting based on the value of the cell in the chart area. |  | Bob | 1
| Formulas define "t" as the current date (red), "x" as the completed portion of a task (gray), |  | Sarah | 2
| and "o" as the incomplete portion of the task (blue). If a value is entered into the Color column, |  | Bill | 3
| that value will be used in place of "o". |  | Jim | 4
5
| Color-coding based on Task Lead |  |  | 6
| One popular reason for color-coding is to help identify ownership of a task. To do this, |  |  | p
| you could create your own nested IF formula: =IF(ref="Bob","o",If(ref="Sally","p","")) |  |  | g
| where "ref" is the reference to the cell in the Lead column. If you want to use the table listed |  |  | k
| to the right of this help section, you can use the following formula in the Color column: |  |  | r
| =IFERROR( INDEX( lead_color, MATCH( ref, lead, 0) ), "") |  |  | o
y
Color-coding based on Urgency or Slippage
| You can enter a formula in the Color column to display the incomplete portion as orange based |  |  | Urgency (Days)
| on a comparison of the End date and Today's date. For example, the formula below would give |  | red | 2
| you a 10 day warning: =IF(end_date < TODAY() + 10, "o" , "") |  | orange | 14
| The example below makes the 10-day warning orange and a 2-day warning red. |  | yellow | 28
= IF(end_date < TODAY() + 2,"r",IF(end_date < TODAY() + 10,"o",""))
Below the Template Rows section in the GanttChart worksheet, you'll find a few color-coding
formulas that you can copy and paste that use the two tables to the right of this help section.
Frequently Asked Questions
Q: | How do I display or "unhide" hidden rows or columns?
To display a hidden row, select the row above and below the rows you want to display.
Right-click on one of the selected row numbers and then choose Unhide.
Tip: to quickly select the column of the currently selected cell, press Ctrl+Spacebar
Q: | My project spans 2 years. How do I print the entire chart without scrolling?
Sorry, but you can't do that without first adding columns to the display range of the
Gantt chart. There is a video on the support page showing how to do this.
View the Video
Q: | How do I use Grouping?
You can expand or collapse a group of rows using Excel's "Group and Outline" feature.
To define a group of rows, select the rows and go to Data > Group
Q: | How do I change the Print Settings?
Select the entire range of cells you want to print and go to Page Layout > Print Area > Set Print Area
Open the Page Setup dialog box to adjust the Scaling, such as fitting to 1 page wide.
Q: | The Start date, End date, or %Complete for the Level 1 task is wrong. How do I fix it?
By default, the Level 1 tasks are set up to show the completion status for all sub tasks
combined. Inserting and re-ordering rows may often mess up these formulas. You may
need to edit the formula to make sure that the correct cells are referenced.
Q: | How can I display week numbers (e.g. 2011-W05-3) for the labels in the chart area?
For U.S. week numbering, you can place the following formula in cell P10 and then
copy that cell to the right.
=YEAR(P9)&" - "&"W"&TEXT(WEEKNUM(P9,1),"00")&" - "&WEEKDAY(P9,1)
For ISO week numbering, the formula would be:
=YEAR(P9)&" - "&"W"&TEXT(1+INT((P9-DATE(YEAR(P9+4-WEEKDAY(P9+6)),1,5)+WEEKDAY(DATE(YEAR(P9+4-WEEKDAY(P9+6)),1,3)))/7),"00")&" - "&WEEKDAY(P9,2)
See this article on week numbering in Excel
Q: | Can I add more color codes?
Yes, but you'll need to create your own set of conditional formats. If you've been rearranging
rows a lot, the set of conditional formats can get pretty messed up, so look at a fresh
copy of this template to see how the conditional formats are set up. Go to Conditional Formatting
and select Manage Rules and choose This Worksheet from the drop-down.
Q: | How do I calculate the % Complete for a level 1 task that contains other summary tasks?
If WBS 1.2 is calculating the % Complete for its own set of sub tasks, 1.2.1, 1.2.2, 1.2.3, etc.
then when calculating the overall % Complete for the top-level 1 task, you would need to exclude
task 1.2's sub tasks, or risk double-counting them. The % Complete formula for the level 1 task
would get complicated, so the easiest thing is to avoid calculating the % Complete for task 1.2.
For task 1.2, you can still use MIN() and MAX() for the start and end dates, but delete the
formula for the % Complete.
The following is an example of a Level 1 task that calculates the % Complete for a non-contiguous
range of tasks:
= ( SUMPRODUCT(days1, pdone1) + SUMPRODUCT(days2, pdone2) ) / SUM(days1, days2)
where days1, days2, pdone1 and pdone2 are references to ranges of cells in the Work Days
and % Done columns.
Note on C2: See the Terms Of Use worksheet and the license agreement on Vertex42.com for information about terms of use, copyright, warranties, and disclaimers. Removing copyright notices is illegal.
Note on C25: This is an example comment.

## TermsOfUse
Terms of Use
© 2006-2014 Vertex42 LLC. All rights reserved.
This template is considered a copyrighted work under the United States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
Not for Resale or Public Sharing
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
Limited Private Sharing
Provided that you observe the above terms, you may share your edited version of this template *privately* with those specific people who **require** access to it within your immediate family, organization, team, or company.
* "Privately" means only accessible to those few people who you expressively give permission to view or edit your file. It is your responsibility to ensure that adequate security measures are used so that your file is not available to the public.
** Examples of acceptable private sharing with people who "require access" may include (a) sharing a budget spreadsheet with a spouse, (b) sharing a project schedule with your project team, or (c) sharing a timesheet with your employee or manager.
Note: If your project team includes an individual outside your organization or company who requires access to the template: Before you share the file you must obtain a written statement from the individual (via email for example) that they agree to only use the template in connection with your specific project and that if they wish to use the template for another purpose, they understand that they must purchase their own license.
See the following page on Vertex42.com for the complete license agreement and examples of other allowed uses:
http://www.vertex42.com/licensing/EULA_privateuse.html
Disclaimer
This template is provided for informational or educational use only and is not intended to be relied on as medical, financial, legal, or other professional advice.
Vertex42 LLC makes no guarantee or representations about this template, or the accuracy or completeness of the content contained within this template.
Vertex42 LLC encourages you to seek the aid of a qualified professional before making decisions regarding health, financial, or legal issues.
Note on A3: Limited Warranty THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." If you purchased this template from Vertex42.com through CLICKBANK, we warrant that for a period of 60 days after delivery of the Software to you, we will return the price you paid upon your request, provided that you destroy all copies of the Software and Documentation in your possession. VERTEX42, LLC EXPRESSLY DISCLAIMS ALL OTHER REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Some states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.